# TESDA-GTZ PROJECT UPDATES

April to June 1999

Based on the Operational Plan for 1999,   activities scheduled for the second quarter of the year were undertaken,  both by the GTZ Project Office and the Office of Apprenticeship.  These were done in close coordination with the different stakeholders of the Project,  and in line with the budget allocations for 1999 as agreed upon by the Project Office and its TESDA  partners.

As a matter of strategy,  all TESDA offices were enjoined by its top management to adopt dual training as a mode of service delivery.  In their work programs for this year,  projects and activities on dual training were specified,  and these were allocated corresponding support from the Project.  Support was provided in terms of the following :

Foreign and Local Short-term Consultants

International Fellowships and Training Programs in Germany

and  Asian Countries

Local Seminars and Workshops

Teaching Materials/Equipment, Studies and Publications

Activities  for the succeeding quarter were lined up in consonance with the 1999 Operational Plan.

## Short-term Consultants

To reinforce existing capabilities on the specialized areas of dual training,  preparations were made to engage foreign and local consultants on the following:

- Dualization of Curricula – German consultant for hiring in October 1999

- Project Monitoring and Evaluation – German consultant for hiring in late November or early December 1999

- Project proposal to combine technical and financial assistance on dual training – local consultant to assist in the development of the proposal.

- Support to training programs in the agriculture sector – a German CIM consultant was requested and  assigned to  Region 3.

At the same time,   local consultancy was provided for implementation of dual training based on Memoranda of Agreement and in coordination with the regional offices,  specifically in the following schools/TESDA training center :

- Concordia College,  NCR

- Mary Help of Christians School,  Pampanga/Region III

- Rogationist Academy,  Cavite/Region IV

- TESDA Region VIII (Tacloban) Training Center– promotion assistance in the form of resource person services.

## International Fellowships and Training Programs

The following international fellowships and training programs,  held in Germany and countries in the Asian region, were sourced and sponsored by the Project in coordination and with funding support from the DSE to enhance the capability of Dual Training service providers :

Title					Duration/Venue	Participants

1.  Electrical Engineering,				April-Sept., 1999		Two Sisters who are

Special Field: Industrial Electronics		DSE-Mannheim                   trainers’ trainors from

Mary Help of Christians

School

2.  Planning, Organization and Implementation	Mar. 15-Apr. 15, 1999	Two TESD Specialists of

of TVET for Women				DSE-Mannheim		TESDA, and one staff from

Concordia College

3.  Jewelry Training				May 23-Sept. 25, 1999	One participant from

DSE-Mannheim		Cottage Industry and

Technology Center

4.  Seminar/Workshop on Moderation		May 24-28, 1999		Two participants from

Techniques					Hua Hin, Thailand	TESDA and one GTZ

Project staff

5.  Effectiveness and Efficiency of TVET		June 16-July 14, 1999	One participant each from

DSE-Mannheim	Punlaan School, Mary   Help Of Christians School,

Concordia College &  NEDA

6.  Trainors’ Training Program in			April 12-18, 1999		Two TESD Specialists

Industrial HRD  School- 			Manila, Philippines	 from  TESDA- OA

Industry Linkages

Preparations were likewise done for attendance to the following programs :

1.  Educational Planing and Research		July 15-Nov. 15, 1999	Two participants from

in Technical and Vocational			DSE-Mannheim		TESDA-PO and TESDA-

Education and Training							 CARAGA

2. Workshop on Management Information		August 9-20, 1999	 One TESD Specialist and

System for Development Projects			University of Bonn,	one IT Officer from TESDA

Germany		 and one GTZ Project staff

3. Special Training Program for Dual Training	Aug. 29-Sept. 11,	 ’99         11 participants coming

Promoters, Implementors and			              			 from TESDA and 8 from

Administrators								 the private sector (TEP).

4.  Special Training Program for the TESDA		 Aug. 22-Oct. 9, ’99	  8 TEP members who

TEP members from the construction					  are from the construction

sector								  sector.

## Local Seminars/Workshops

# The National Institute for Technical-Vocational Education and Training (NITVET) implemented one batch of Seminar-Workshop on Regional Implementation of Dualized Curricula on May 17 – 21, 1999.  It was designed and conducted in coordination with the Office of Apprenticeship (OA),  with  the active participation of the CIM consultant.  The program objectives were successfully achieved in this initial batch,  and preparations went underway for the conduct of additional two batches.  These had been scheduled for implementation within the next quarter, with funding support equally shared by the GTZ Project Office and the Office of Apprenticeship.

In line with ensuring qualification of Dual Training teachers/trainors  and Industrial Coordinators,  the Project has committed to support the regional TESDA offices in the conduct of  DT Teachers’/Trainors Courses.  Region III conducted a program in May 1999 wherein the GTZ Project staff gave support .  TESDA-ARMM likewise prepared a proposal which is currently being evaluated jointly by the Project Office and the Office of Apprenticeship.  It is targeted for implementation within the next quarter.

Complementing the various in-house programs on DT is the Industrial Coordinators Development Program,  one of the major programs of the OA.  It involves the design and implementation of  basic and advanced courses for industrial coordinators.  Although the target date of implementation is November of this year,  preparatory activities such as project organization,  course design and materials development  have already been started.

Staff development program for the Office of Apprenticeship, the focal office for Dual Training, was planned within this period,  based on the  identified top priority training needs : (1) skills development on the ZOPP methodology and (2) teambuilding.  The Project  committed to support this program which has been scheduled for implementation in September 1999.

## Teaching Materials/Equipment, Studies and Publications

The Project Office continued to provide assistance to improve the capability of schools/training institutions participating in dual training.  Complete sets of learning equipment were distributed to the following TESDA  Central and Regional offices :

OA		A metaplan training kit

NCR		A metaplan training kit for the Regional Office ;

The Concordia College virtual office was turned over to the school’s administrators.  Likewise ,  the final report for Phase I of the Dual Training Pilot Program was presented  and discussed in the presence of the OA Division Chief,  NCR District Director, guests  from Concordia and the private sector, and the GTZ staff.  This contains the plan and strategies to operationalize the dualized curricula within the virtual office situation.

Region 3	10 units oscilloscope for distribution to Training

Centers within the Region ;

Region 4	 GTZ Vocational Books Programme 1997/98

consisting of 60 instructional materials for the

Electronics,  Electrical Engineering,  Metal Trade

and Automotive Engineering sectors ;

A metaplan training kit for the Regional Office.

Region 11	 Electro Pneumatic Hardware component and

Proximity Sensors (Inductive, Capacitive, Optical)

from Germany.

These sets of equipment were requested by the regional offices in line with the implementation of dual training programs included in their respective workplans for this year.

Other Activities

Project Management

Important developments  relative to internal efficiency took place within this period .  Foremost was the assumption to duty of the Senior Technical Consultant of the Project,  Mr. Heinz-Dieter Harbers.

In addition,  the Project Manager accomplished major assignments relative to the present and future cooperation efforts within the context of the Project.  He went on official trip to Germany for a final discussion of the Project Progress Review (PPR) report together with the Appraisers.

The following workshops were attended by the GTZ staff :

- Workshop  involving all GTZ projects in the Philippines,  and

- NEDA Workshop on the Philippine-German Technical Cooperation

To maximize the use of resources, the project management sustained earlier initiatives to coordinate  promotion activities with other German agencies concerned with Dual Training (CIM,  DED and LIB).

Planned Activities for the Next Quarter

With the scheduled holding of the DTS Congress in October,  the months of July,  August and September will be heavy with preparatory promotional activities.  It is within these months when all promotional data and information will be packaged for marketing  to all stakeholders and prospective champions of Dual Training.

In terms of Project operational plans, the third quarter of the year shall be a peak period  as the following major activities are expected to take off :

- Staff Development Program for the Speakers’ Bureau

- Documentation of Pilot Programs

- Regionalization of Dualized Curricula

- Advanced Training of Dual Training Promoters,  Implementors and Administrators

- Operationalization of the Project Monitoring and Evaluation System

- Integration and Coordination of German Agency Programs on Dual Training in the Philippines

- Procurement of learning materials for different TESDA offices nationwide.

Within this context,  the Project Management  Office has positioned its resources to meet the planned and expected demands of its environment.